## Epics Overview
FLEXMATCHES — EPIC OVERVIEW
Epic ID | Epic Name | MVP Phase | Sprint Range | Total Stories | Total Points | Must Have | Should Have
E01 | Critical Error Handling | MVP-0 | Eagle 0 | 4 | 21 | 4 | 0
E02 | Data Safety & Destructive Actions | MVP-0 | Eagle 0–Eagle 1 | 3 | 13 | 2 | 1
E03 | Auth & Onboarding Fixes | MVP-0 | Eagle 0–Eagle 1 | 5 | 18 | 2 | 3
E04 | Streak & Trust Mechanics | MVP-0 | Eagle 0 | 2 | 8 | 2 | 0
E05 | Notification Completeness | MVP-1 | Eagle 2 | 5 | 17 | 5 | 0
E06 | Trust System Unification | MVP-1 | Eagle 3 | 3 | 13 | 1 | 2
E07 | Security & App Store Compliance | MVP-2 | Eagle 3 | 4 | 19 | 4 | 0
E08 | Theme & Visual Consistency | MVP-2 | Eagle 4 | 4 | 18 | 0 | 4
E09 | Input Validation & UX Polish | MVP-2 | Eagle 4–Eagle 5 | 4 | 11 | 0 | 4
E10 | Accessibility & Growth | MVP-3 | Eagle 5 | 4 | 12 | 0 | 1

## RICE Scoring
FLEXMATCHES — RICE PRIORITIZATION
Story ID | Title | Reach (1-10) | Impact (0.25-3) | Confidence (0-1) | Effort (weeks) | RICE Score | MoSCoW | Story Points | Sprint | Rank
FM-502 | Swipe-Mode Like Sends Push Notification | 9 | 3 | 1 | 0.5 | 54 | Must Have | 2 | Eagle 2 | 1
FM-505 | Push Token Cleanup on Logout | 8 | 2 | 1 | 0.5 | 32 | Must Have | 2 | Eagle 2 | 2
FM-402 | Quick Check-in Spam Prevention | 9 | 3 | 1 | 1 | 27 | Must Have | 3 | Eagle 0 | 3
FM-703 | Search Input Sanitization (Injection Fix) | 10 | 3 | 0.8 | 1 | 24 | Must Have | 3 | Eagle 3 | 4
FM-103 | React Error Boundary in Root Layout | 10 | 2 | 1 | 1 | 20 | Must Have | 3 | Eagle 0 | 5
FM-303 | Onboarding Skip Guardrails | 8 | 2 | 1 | 1 | 16 | Should Have | 3 | Eagle 1 | 6
FM-504 | Realtime Subscription User Filter (Security) | 10 | 3 | 0.8 | 1.5 | 16 | Must Have | 4 | Eagle 2 | 7
FM-201 | Separate Delete Messages from Unmatch | 10 | 3 | 1 | 2 | 15 | Must Have | 5 | Eagle 0 | 8
FM-301 | Forgot Password Flow | 10 | 3 | 1 | 2 | 15 | Must Have | 5 | Eagle 0 | 9
FM-302 | Fix Onboarding Race Condition | 10 | 3 | 1 | 2 | 15 | Must Have | 5 | Eagle 0 | 10
FM-401 | Streak Consecutive Day Enforcement | 10 | 3 | 1 | 2 | 15 | Must Have | 5 | Eagle 0 | 11
FM-203 | Duplicate Match Request Prevention | 7 | 2 | 1 | 1 | 14 | Should Have | 3 | Eagle 1 | 12
FM-603 | Date Pickers Replace Raw Text (Sessions, Goals, Challenges) | 7 | 2 | 1 | 1 | 14 | Should Have | 3 | Eagle 3 | 13
FM-102 | Chat Message Send with Error Recovery | 9 | 3 | 1 | 2 | 13.5 | Must Have | 5 | Eagle 0 | 14
FM-304 | Password Confirmation & Strength Validation | 8 | 2 | 0.8 | 1 | 12.8 | Should Have | 3 | Eagle 1 | 15
FM-503 | Session Proposal & Response Notifications | 8 | 3 | 0.8 | 1.5 | 12.8 | Must Have | 4 | Eagle 2 | 16
FM-305 | Email Validation & Navigation Stack Fix | 6 | 1 | 1 | 0.5 | 12 | Should Have | 2 | Eagle 1 | 17
FM-901 | Negative Value Validation (Age/Weight/Duration/Progress) | 6 | 1 | 1 | 0.5 | 12 | Should Have | 2 | Eagle 4 | 18
FM-501 | Push Notification Tap Deep Linking | 9 | 3 | 0.8 | 2 | 10.8 | Must Have | 5 | Eagle 2 | 19
FM-101 | Global Error Handling on All Screen Load Functions | 10 | 3 | 1 | 3 | 10 | Must Have | 8 | Eagle 0 | 20
FM-801 | Dark/Light Theme Audit — All Hardcoded Colors | 10 | 2 | 1 | 2 | 10 | Should Have | 5 | Eagle 4 | 21
FM-804 | SwipeDeck PanResponder Fix (Allow Card Taps) | 9 | 2 | 0.8 | 1.5 | 9.6 | Should Have | 3 | Eagle 4 | 22
FM-704 | Terms & Privacy Policy (Tappable Links + Real Documents) | 8 | 2 | 0.8 | 1.5 | 8.5 | Must Have | 3 | Eagle 3 | 23
FM-1002 | Google Places Autocomplete for City | 8 | 2 | 0.8 | 1.5 | 8.5 | Should Have | 3 | Eagle 5 | 24
FM-903 | Loading States on All Async Buttons | 8 | 1 | 1 | 1 | 8 | Should Have | 3 | Eagle 4 | 25
FM-1003 | Circle Capacity Enforcement | 4 | 1 | 1 | 0.5 | 8 | Could Have | 2 | Eagle 5 | 26
FM-1004 | Ended Challenges Block Progress Updates | 4 | 1 | 1 | 0.5 | 8 | Could Have | 2 | Eagle 5 | 27
FM-902 | Keyboard Handling on All Modals | 7 | 1 | 1 | 1 | 7 | Should Have | 3 | Eagle 4 | 28
FM-904 | useFocusEffect on Stale Screens | 7 | 1 | 1 | 1 | 7 | Should Have | 3 | Eagle 5 | 29
FM-202 | Account Deletion with Full Auth Cleanup | 8 | 3 | 0.8 | 3 | 6.4 | Must Have | 5 | Eagle 1 | 30
FM-601 | Unified Tier System (Single Source of Truth) | 8 | 2 | 0.8 | 2 | 6.4 | Must Have | 5 | Eagle 3 | 31
FM-803 | Discover Pagination (Replace 80-User Hard Cap) | 8 | 2 | 0.8 | 2 | 6.4 | Should Have | 5 | Eagle 4 | 32
FM-701 | iOS In-App Purchase for Pro Subscription | 10 | 3 | 0.8 | 4 | 6 | Must Have | 8 | Eagle 3 | 33
FM-702 | Admin Actions to Supabase Edge Functions | 5 | 3 | 0.8 | 2 | 6 | Must Have | 5 | Eagle 3 | 34
FM-104 | Session Action Error Handling | 7 | 2 | 0.8 | 2 | 5.6 | Must Have | 5 | Eagle 0 | 35
FM-602 | Mutual Session Confirmation | 7 | 2 | 0.8 | 2 | 5.6 | Should Have | 5 | Eagle 3 | 36
FM-802 | Messages N+1 Query Optimization | 7 | 2 | 0.8 | 2 | 5.6 | Should Have | 5 | Eagle 4 | 37
FM-1001 | Accessibility Labels on All Interactive Elements | 3 | 2 | 0.8 | 2 | 2.4 | Could Have | 5 | Eagle 5 | 38

## Backlog (JIRA)
FLEXMATCHES — PRODUCT BACKLOG (JIRA-Style)
Key | Type | Epic | Summary | User Story | MoSCoW | Priority | Points | Sprint | Assignee | Status | Acceptance Criteria (Given/When/Then) | QA Verification Tasks | QA DoD Checklist | UI/Design Requirements | Story-Specific DoD (beyond standard)
E01 | Epic | — | Critical Error Handling | Epic: Critical Error Handling
FM-101 | Story | E01 | Global Error Handling on All Screen Load Functions | As a user, I want every screen to recover gracefully from network failures, so that I never see an infinite loading spinner with no escape. | Must Have | P0 | 8 | Eagle 0 | Senior Dev | To Do | AC1: Given any of these 10 screens is loading data: Home, Discover, Messages, Matches, Profile, Feed, Activity, Goals, Leaderboard, Challenges — When a Supabase query fails or network is unavailable, Then the ErrorState component (from FM-103) is shown with 'Try Again' button AC2: Given the ErrorState is displayed on a screen, When the user taps 'Try Again', Then the load() function re-invokes, the ErrorState disappears, and the skeleton loader appears AC3: Given a retry also fails, When the error occurs again, Then the ErrorState shows again (no infinite retry loop, no infinite skeleton) AC4: Given a screen uses pull-to-refresh (RefreshControl), When the refresh fails, Then the existing data stays on screen (NOT replaced by ErrorState), and a toast shows 'Could not refresh. Please try again.' AC5: Given any screen's load() function, When inspecting the code, Then every Promise.all is wrapped in try/catch, errors are logged with screen name prefix (e.g. '[Home] load failed'), and setLoading(false) is in a finally block AC6: Given a skeleton loader is displayed, When 15 seconds pass without data or error, Then the ErrorState is shown automatically (timeout fallback) | QA must verify error state on ALL 10 screens: ☐ 1. Home (app/(tabs)/home.tsx) ☐ 2. Discover (app/(tabs)/discover.tsx) ☐ 3. Messages (app/(tabs)/messages.tsx) ☐ 4. Matches (app/(tabs)/matches.tsx) ☐ 5. Profile (app/(tabs)/profile.tsx) ☐ 6. Feed (app/(tabs)/feed.tsx) ☐ 7. Activity (app/(tabs)/activity.tsx) ☐ 8. Goals (app/(tabs)/goals.tsx) ☐ 9. Leaderboard (app/(tabs)/leaderboard.tsx) ☐ 10. Challenges (app/(tabs)/challenges.tsx) Per screen test steps: • Turn on airplane mode → open screen → verify ErrorState shows • Tap 'Try Again' with network restored → verify data loads • Pull-to-refresh with network off → verify existing data stays + toast appears • Verify no console errors or unhandled promise rejections • Verify skeleton loader never shows longer than 15 seconds | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Uses ErrorState component from FM-103 (must be designed first) • Error state must be visually consistent across all 10 screens • Skeleton → ErrorState transition: no flash, smooth replace • Pull-to-refresh failure toast: standard toast style Designer delivers: • Approve ErrorState placement in each screen type (scrollable vs fixed) • Toast design for refresh failures ⚠️ DEPENDENCY: FM-103 must be completed first (creates ErrorState.tsx) | ☐ All 10 screens have try/catch in load() ☐ Each screen uses ErrorState from components/ui/ErrorState.tsx ☐ Each screen has 3 states: loading (skeleton), success (data), error (ErrorState) ☐ Pull-to-refresh failure shows toast, does NOT replace existing data ☐ Skeleton timeout of 15 seconds triggers ErrorState ☐ Error logs include screen name prefix: '[Home] load failed:' ☐ setLoading(false) is in finally block (not in try or catch) ☐ ErrorState tested on all 10 screens in BOTH themes ☐ No unhandled promise rejections in console ☐ Retry from ErrorState successfully loads data when network returns ⚠️ BLOCKER: Cannot start until FM-103 (ErrorState component) is Done
FM-102 | Story | E01 | Chat Message Send with Error Recovery | As a user, I want my typed message preserved if sending fails, so that I don't lose what I wrote. | Must Have | P0 | 5 | Eagle 0 | Senior Dev | To Do | AC1: Given I have typed a message in chat, When I tap send and the Supabase insert fails, Then my typed text remains in the input field and a toast says 'Message failed to send' AC2: Given a message failed to send, When I see the failed message indicator, Then I can tap retry to re-attempt the insert with the same content AC3: Given I tap send, When the async operation is in progress, Then the send button shows a spinner and is disabled to prevent double-send | • Verify text is NOT cleared from input until insert returns success • Verify failed message shows red error indicator in chat list • Verify double-tap on send does not create duplicate messages • Verify retry on failed message successfully sends when network is restored | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Failed message indicator (red icon/border in chat bubble) • Retry affordance on failed message • Send button loading spinner style Designer delivers: Failed message state mockup | ☐ Failed message shows distinct visual indicator ☐ Retry action is discoverable ☐ Send button loading state prevents double-send ☐ Original text preserved in input on failure ☐ Toast/alert message copy reviewed by PO
FM-103 | Story | E01 | React Error Boundary in Root Layout | As a user, I want the app to show a recovery screen instead of crashing, so that I can continue using the app after an unexpected error. | Must Have | P0 | 3 | Eagle 0 | Mid Dev | To Do | AC1: Given any unhandled JavaScript error occurs in the component tree, When the error propagates to the root layout, Then a full-screen error view shows with 'Something went wrong' and a 'Restart' button AC2: Given the error screen is displayed, When I tap 'Restart', Then the error boundary resets and the app re-renders to the last working screen AC3: Given any crash scenario, When the error screen appears, Then no raw error text, stack traces, or technical jargon are visible to the user AC4: Given a network error (not a JS crash), When a screen's load() fails, Then the Error Boundary does NOT trigger — individual screen ErrorState handles it instead AC5: Given the ErrorState component is created, When it renders, Then it uses theme colors (useTheme), accepts onRetry callback, and shows icon + message + 'Try Again' button | • Trigger a deliberate JS error by adding `throw new Error('test')` in a component render — verify boundary catches it • Verify restart button recovers the app to Home screen in usable state • Verify error is logged to console (console.error) for debugging • Verify no user-facing technical jargon in the error screen • Verify network errors do NOT trigger the error boundary (they use ErrorState instead) • Verify ErrorState component renders correctly in BOTH dark and light themes • Verify ErrorState 'Try Again' button has loading state while retrying | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED (2 components): 1. ErrorBoundary crash screen: • Full-screen centered layout • Illustration or icon (⚠️ or custom) • Title: 'Something went wrong' • Subtitle: 'The app ran into an unexpected problem' • 'Restart' button (primary style) • Must NOT show any error details 2. ErrorState reusable component: • Centered in parent container (not full-screen) • Error icon • Message: 'Something went wrong' (customizable via prop) • 'Try Again' button with loading state • Both themes supported Designer delivers: Mockup of BOTH components before dev starts | ☐ ErrorBoundary wraps root navigation in _layout.tsx ☐ ErrorBoundary catches JS crashes → shows crash screen ☐ ErrorState.tsx created at components/ui/ErrorState.tsx ☐ ErrorState accepts: onRetry, message (optional) props ☐ ErrorState uses useTheme() — zero hardcoded colors ☐ Restart button recovers app to usable state ☐ No raw error text or stack traces visible to user ☐ Error logged to console for debugging ☐ Both components look correct in dark AND light theme ☐ Network errors do NOT trigger ErrorBoundary
FM-104 | Story | E01 | Session Action Error Handling | As a user, I want session actions to confirm success before updating the UI, so that I always know the real status of my sessions. | Must Have | P0 | 5 | Eagle 0 | Senior Dev | To Do | AC1: Given I tap Accept/Decline/Cancel/Confirm on a session, When the Supabase update returns an error, Then a toast shows 'Could not update session. Please try again.' and the UI state remains unchanged AC2: Given I tap any session action button, When the async call is in progress, Then the button shows a loading spinner and is disabled AC3: Given I rapidly tap an action button twice, When the first request is in-flight, Then only one server request is made | • Verify all 5 session actions (propose/accept/decline/cancel/confirm) handle errors • Verify UI does not change until server confirms success • Verify double-tap prevention on all session action buttons | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • Loading spinner on session action buttons (Accept/Decline/Cancel/Confirm) • Disabled button state during async • Use existing button patterns Designer review: Not needed (uses existing patterns) | ☐ All 5 session actions handle errors with toast ☐ UI does NOT change until server confirms ☐ Double-tap prevention verified ☐ Button re-enables after failure
E02 | Epic | — | Data Safety & Destructive Actions | Epic: Data Safety & Destructive Actions
FM-201 | Story | E02 | Separate Delete Messages from Unmatch | As a user, I want 'Delete messages' and 'Unmatch' to be completely separate actions with confirmation, so that I never accidentally lose a connection. | Must Have | P0 | 5 | Eagle 0 | Senior Dev | To Do | AC1: Given I swipe left on a conversation and tap 'Delete messages', When the confirmation dialog appears, Then it says 'Delete all messages with [Name]? The match will be preserved.' and only deletes messages, not the match AC2: Given I swipe left on a conversation and tap 'Unmatch', When the confirmation dialog appears, Then it says 'Unmatch [Name]? This will permanently remove this connection and all messages. This cannot be undone.' AC3: Given I tap 'Cancel' on either confirmation dialog, When the dialog closes, Then no data is changed and the conversation remains as-is AC4: Given I confirm 'Unmatch', When the action completes, Then the match status is set to 'unmatched' (distinct from 'declined') | • Verify 'Delete messages' only removes messages, match row preserved • Verify 'Unmatch' sets status='unmatched' not 'declined' • Verify both actions show confirmation dialog before executing • Verify Cancel on dialog makes no data changes • Verify swipe actions are clearly labeled and visually distinct | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Confirmation dialog copy for 'Delete Messages' • Confirmation dialog copy for 'Unmatch' • Distinct visual treatment for the two swipe actions • Destructive action uses red styling Designer delivers: Dialog copy + swipe action layout | ☐ 'Delete messages' only removes messages (match preserved) ☐ 'Unmatch' uses status='unmatched' not 'declined' ☐ Both dialogs have Cancel option ☐ Dialog copy reviewed and approved by PO ☐ Destructive button uses red/warning color
FM-202 | Story | E02 | Account Deletion with Full Auth Cleanup | As a user, I want account deletion to fully remove my data including auth credentials, so that I cannot log back in to a broken state. | Must Have | P0 | 5 | Eagle 1 | Senior Dev | To Do | AC1: Given I tap 'Delete Account' in Settings, When the first dialog appears, Then it asks 'Are you sure? This permanently deletes all your data.' AC2: Given I confirm the first dialog, When the second confirmation appears, Then I must type 'DELETE' to proceed AC3: Given I confirm both dialogs, When the Edge Function executes, Then it deletes: profile row, push tokens, AND auth.users entry via auth.admin.deleteUser() AC4: Given deletion succeeds, When I try to log in with the same email, Then authentication fails with 'No account found' AC5: Given deletion fails (network error), When the error is shown, Then the Delete button re-enables and I can try again | • Verify two-step confirmation (dialog + type DELETE) • Verify Edge Function deletes profile, tokens, and auth user • Verify re-login with deleted email fails • Verify delete button re-enables on failure (not stuck disabled) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Two-step deletion confirmation flow • Type 'DELETE' input design • Account deletion success state Designer delivers: Deletion flow mockup | ☐ Two-step confirmation works ☐ Edge Function deletes profile + tokens + auth ☐ Re-login with deleted email fails ☐ Delete button re-enables on failure
FM-203 | Story | E02 | Duplicate Match Request Prevention | As a user, I want the app to prevent me from sending duplicate match requests, so that I don't accidentally spam someone. | Should Have | P1 | 3 | Eagle 1 | Mid Dev | To Do | AC1: Given I have already sent a match request to User B, When I view User B's card in Discover or Search, Then the connect button shows 'Pending' instead of 'Connect' AC2: Given User B has already accepted my match, When I view User B's card, Then the button shows 'Connected' and tapping opens chat AC3: Given I tap Connect, When the request is being processed, Then the button immediately disables and shows a loading spinner | • Verify no duplicate rows in matches table for same user pair • Verify button state reflects actual match status • Verify this works across all connect entry points (Discover, Search, ProfileSheet) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • 'Pending' and 'Connected' button states Designer review: Button state variants | ☐ No duplicate rows in matches table ☐ Button reflects actual match status ☐ Works across all connect entry points
E03 | Epic | — | Auth & Onboarding Fixes | Epic: Auth & Onboarding Fixes
FM-301 | Story | E03 | Forgot Password Flow | As a returning user who forgot my password, I want to reset it via email, so that I can regain access to my account. | Must Have | P0 | 5 | Eagle 0 | Mid Dev | To Do | AC1: Given I am on the login screen, When I look below the password field, Then I see a 'Forgot password?' link AC2: Given I tap 'Forgot password?' and enter my email, When I tap 'Send Reset Link', Then supabase.auth.resetPasswordForEmail() is called and I see 'Check your email for a reset link' AC3: Given I enter an invalid or unknown email, When I tap send, Then I see a safe error message (no account enumeration) AC4: Given I tap the reset link in my email, When the app opens, Then I land on a password reset screen where I can set a new password | • Verify forgot password link is visible and tappable on login screen • Verify reset email is sent for valid accounts • Verify error handling for invalid/unknown emails • Verify deep link from email opens password reset screen • Verify new password works for subsequent login | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Forgot Password screen layout (email input + send button) • Success state ('Check your email') • Error state (invalid/unknown email) • 'Forgot password?' link placement on login screen Designer delivers: Forgot password screen mockup + link placement | ☐ Forgot password link visible on login screen ☐ Reset email sends for valid accounts ☐ Error message is safe (no account enumeration) ☐ Success state is clear and actionable ☐ Deep link from email opens reset screen
FM-302 | Story | E03 | Fix Onboarding Race Condition | As a new user, I want to always land on onboarding after registration, so that my profile gets set up before I enter the app. | Must Have | P0 | 5 | Eagle 0 | Senior Dev | To Do | AC1: Given I just completed registration, When the auth state changes, Then routing is handled centrally in _layout.tsx using a needsOnboarding flag AC2: Given needsOnboarding is true, When the auth listener fires, Then I am routed to onboarding (not home), regardless of timing AC3: Given I complete onboarding and tap 'Let's go', When the profile save succeeds, Then needsOnboarding is set to false and I navigate to home AC4: Given the profile save fails during onboarding, When the error occurs, Then an Alert shows, I stay on the current step, and my entered data is preserved in state | • Verify new signup always lands on onboarding (test 10 times for race condition) • Verify existing user login bypasses onboarding • Verify network failure during onboarding save shows error and preserves data • Verify profile data actually persists in Supabase after successful onboarding | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: • This is a routing/logic fix — no visual changes • Onboarding save failure shows standard Alert Designer review: Not needed | ☐ New signup ALWAYS lands on onboarding (test 10x) ☐ Existing user bypasses onboarding ☐ Network failure during save shows Alert + preserves data ☐ Profile data persists in Supabase after success ☐ No race condition between auth listener and register
FM-303 | Story | E03 | Onboarding Skip Guardrails | As a new user, I want the app to require at least my name, so that I have a functional profile that others can see. | Should Have | P1 | 3 | Eagle 1 | Mid Dev | To Do | AC1: Given I am on onboarding step 1 (Name), When I look for the Skip button, Then it is not visible or is disabled AC2: Given I am on step 1, When I try to proceed without entering a name, Then the Continue button is disabled and I see a hint 'Name is required' AC3: Given I am on steps 2-5, When I tap Skip, Then partial progress (data entered so far) is saved before advancing | • Verify Skip is hidden/disabled on step 1 • Verify name field requires 2-50 characters (trimmed) • Verify skipping later steps saves partial progress | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • 'Name is required' hint text placement Designer review: Not needed | ☐ Skip hidden on step 1 ☐ Name requires 2-50 chars ☐ Skipping later steps saves partial progress
FM-304 | Story | E03 | Password Confirmation & Strength Validation | As a new user, I want a confirm password field and strength indicator, so that I create a secure, correct password. | Should Have | P1 | 3 | Eagle 1 | Mid Dev | To Do | AC1: Given I am on the register screen, When I look at the form, Then there is a 'Confirm Password' field below the password field AC2: Given I type a password, When it does not meet requirements (8+ chars, 1 uppercase, 1 number), Then a strength indicator shows 'Weak' in red AC3: Given my passwords match and meet strength requirements, When I look at the Create Account button, Then it is enabled AC4: Given both login and register screens, When I look at the password field, Then there is an eye icon toggle to show/hide the password | • Verify confirm password must match before submission • Verify weak passwords are rejected (test: 'aaaaaa', '123456', 'password') • Verify strength indicator updates in real-time • Verify eye toggle works on both login and register | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Password strength indicator (weak/medium/strong) • Confirm password field placement • Eye toggle icon Designer delivers: Strength indicator mockup | ☐ Confirm password must match ☐ Weak passwords rejected ☐ Strength indicator updates in real-time ☐ Eye toggle works on login + register
FM-305 | Story | E03 | Email Validation & Navigation Stack Fix | As a user, I want email format validated before submission and smooth navigation between login and register, so that I don't waste time on invalid inputs or get confused by stacked screens. | Should Have | P1 | 2 | Eagle 1 | Mid Dev | To Do | AC1: Given I enter an invalid email format (e.g., 'asdfgh'), When I tap submit or blur the field, Then I see an inline error 'Please enter a valid email address' AC2: Given I toggle between Login and Register, When I navigate, Then router.replace() is used (no screen stacking — back button goes to Welcome, not previous auth screen) | • Verify invalid emails are rejected client-side before API call • Verify navigating login↔register 5 times doesn't stack 5 screens • Verify back button from login/register goes to Welcome | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Logic/validation only | ☐ Invalid emails rejected client-side ☐ No screen stacking on login↔register ☐ Back goes to Welcome
E04 | Epic | — | Streak & Trust Mechanics | Epic: Streak & Trust Mechanics
FM-401 | Story | E04 | Streak Consecutive Day Enforcement | As a user, I want my streak to accurately reflect consecutive workout days, so that I can trust the number I see on my profile. | Must Have | P0 | 5 | Eagle 0 | Senior Dev | To Do | AC1: Given I logged a workout yesterday (local time), When I log a workout today, Then my streak increments by 1 AC2: Given I logged a workout 2+ days ago, When I log a workout today, Then my streak resets to 1 AC3: Given I already logged a workout today, When I try to log again, Then my streak does NOT increment (stays the same) AC4: Given any streak update, When the operation executes, Then it uses a Supabase RPC function (atomic, not read-modify-write) and all date comparisons use local calendar dates (not UTC) | • Verify consecutive day logging increments streak correctly (test 3 consecutive days) • Verify 2-day gap resets streak to 1 • Verify same-day duplicate does not inflate streak • Verify late-night workout (11pm) counts for correct local day, not UTC next day | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: • Streak logic is backend-only (RPC function) • No visual changes to existing streak display Designer review: Not needed | ☐ Consecutive day increments correctly ☐ 2+ day gap resets to 1 ☐ Same-day duplicate does NOT inflate ☐ Uses Supabase RPC (atomic, not read-modify-write) ☐ Late-night workout counts for correct local day
FM-402 | Story | E04 | Quick Check-in Spam Prevention | As a user, I want check-in to only count once per day, so that streaks cannot be gamed and partner notifications stay credible. | Must Have | P0 | 3 | Eagle 0 | Mid Dev | To Do | AC1: Given I have already checked in today, When I look at the Quick Check-in button, Then it shows 'Checked in ✓' and is disabled AC2: Given the check-in is enforced server-side, When any client tries to increment twice, Then the RPC function rejects the duplicate AC3: Given I check in, When partner notifications fire, Then each partner receives max 1 notification per day from me | • Verify tapping check-in 10 times only increments streak by 1 • Verify button state changes to disabled after first check-in • Verify server-side enforcement (test via direct API call) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • Check-in button disabled state ('Checked in ✓') • Use existing disabled button pattern Designer review: Quick review of disabled state | ☐ 10 taps only increments streak by 1 ☐ Button shows 'Checked in ✓' and is disabled ☐ Server-side enforcement works (direct API test) ☐ Partner notifications limited to 1/day
E05 | Epic | — | Notification Completeness | Epic: Notification Completeness
FM-501 | Story | E05 | Push Notification Tap Deep Linking | As a user, I want tapping a push notification to navigate me to the relevant screen, so that I can immediately see what happened. | Must Have | P0 | 5 | Eagle 2 | Senior Dev | To Do | AC1: Given I receive a push notification while the app is backgrounded, When I tap the notification, Then the app opens and navigates to the correct screen (match_request→Matches, new_message→Chat, session→Chat) AC2: Given I tap a notification after the app was killed (cold start), When the app initializes, Then the deep link still routes correctly after auth check AC3: Given each notification, When it is created, Then the payload includes a 'type' field and relevant 'relatedId' for routing | • Verify deep link works from background state for each notification type • Verify deep link works from killed/cold start state • Verify unknown notification types open app to Home (graceful fallback) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Navigation logic only | ☐ Deep link works from background ☐ Deep link works from cold start ☐ Unknown types fallback to Home
FM-502 | Story | E05 | Swipe-Mode Like Sends Push Notification | As a user, I want to be notified when someone likes me in swipe mode, so that I know someone is interested in training with me. | Must Have | P0 | 2 | Eagle 2 | Mid Dev | To Do | AC1: Given User A swipes right on User B in swipe mode, When the match insert succeeds, Then notifyUser() is called for User B with type='match_request' AC2: Given the notification is sent, When User B receives it, Then it says '[Name] wants to connect with you!' | • Verify swipe-right triggers push notification to receiver • Verify notification content includes sender's name • Verify duplicate swipes don't send multiple notifications | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Backend notification wiring | ☐ Swipe-right triggers push ☐ Notification includes sender name ☐ No duplicate notifications
FM-503 | Story | E05 | Session Proposal & Response Notifications | As a user, I want session proposals and responses to notify both sides, so that the session coordination loop is complete. | Must Have | P0 | 4 | Eagle 2 | Mid Dev | To Do | AC1: Given I propose a session, When the insert succeeds, Then my partner receives a push with type='session_proposed' saying '[Name] proposed a workout: [Sport] on [Date]' AC2: Given my partner accepts my session, When the update succeeds, Then I receive a push with type='session_accepted' saying '[Name] accepted your session!' AC3: Given my partner declines, When the update succeeds, Then I receive a push with type='session_declined' saying '[Name] can't make the session' | • Verify session proposal triggers push to partner • Verify session accept triggers push to proposer • Verify session decline triggers push to proposer • Verify all notifications include correct names and session details | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Backend notification wiring | ☐ Proposal notifies partner ☐ Accept notifies proposer ☐ Decline notifies proposer
FM-504 | Story | E05 | Realtime Subscription User Filter (Security) | As a user, I want to only receive realtime events for my own messages, so that other users' message content is never visible to me. | Must Have | P0 | 4 | Eagle 2 | Senior Dev | To Do | AC1: Given I am in a chat screen, When the realtime subscription is created, Then it includes a filter: match_id=eq.${currentMatchId} AC2: Given User A sends a message to User B, When User C is also connected to realtime, Then User C's client never receives User A's message payload | • Verify subscription filter is set correctly in code review • Verify with 2 test accounts that messages don't leak between conversations • Verify realtime still works correctly for the intended conversation | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Security fix only | ☐ Subscription filter set correctly ☐ Messages don't leak between users ☐ Realtime still works for intended conversation
FM-505 | Story | E05 | Push Token Cleanup on Logout | As a user, I want my push tokens removed when I sign out, so that the next person on this device doesn't receive my notifications. | Must Have | P0 | 2 | Eagle 2 | Senior Dev | To Do | AC1: Given I am signed in and have a push token stored, When I tap Sign Out in Settings, Then unregisterPushToken() is called BEFORE signOut() AC2: Given I sign out and another user signs in, When notifications are sent to my account, Then this device does NOT receive them | • Verify push token is removed from DB on logout • Verify token removal happens before auth signout • Verify new user on same device only gets their own notifications | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Backend cleanup logic | ☐ Token removed from DB on logout ☐ Removal happens before signout ☐ New user doesn't get old user's notifications
E06 | Epic | — | Trust System Unification | Epic: Trust System Unification
FM-601 | Story | E06 | Unified Tier System (Single Source of Truth) | As a user, I want my tier label to be consistent on every screen, so that I can trust the gamification system. | Must Have | P0 | 5 | Eagle 3 | Senior Dev | To Do | AC1: Given my profile shows 'Gold' tier, When I open the Leaderboard, Then it also shows 'Gold' tier (same calculation) AC2: Given the tier system, When any screen calculates tier, Then it uses the single calcTier() function from lib/badges.ts AC3: Given the leaderboard, When it was using streak-based tiers (0/50/100/200/500), Then that is removed and replaced with the points-based system | • Verify same user shows identical tier on Profile, Leaderboard, and any other surface • Verify all tier calculation references point to lib/badges.ts • Verify old streak-based tier code is fully removed from leaderboard | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: Verify tier badges look consistent Designer review: Visual consistency check | ☐ Same tier on Profile and Leaderboard ☐ All calculations use lib/badges.ts ☐ Old streak-based tier code removed
FM-602 | Story | E06 | Mutual Session Confirmation | As a user, I want completed-session stats to update fairly, so that one person confirming doesn't credit both without consent. | Should Have | P1 | 5 | Eagle 3 | Senior Dev | To Do | AC1: Given User A confirms a session, When the confirmation saves, Then only User A's confirmed_by flag is set (not both users' stats) AC2: Given both User A and User B have confirmed, When the system checks, Then sessions_completed increments for both users AC3: Given User A reports no-show, When the report saves, Then only User B's sessions_no_show increments (not User A's) AC4: Given any stat update, When it executes, Then it uses an atomic Supabase RPC (not read-modify-write) | • Verify one-sided confirmation only updates confirming user's flag • Verify stats only increment when both users have confirmed • Verify no-show does not penalize the reporter • Verify concurrent confirmations don't lose data (race condition test) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Backend logic only | ☐ One-sided confirm only sets confirming user's flag ☐ Stats increment when BOTH confirm ☐ No-show doesn't penalize reporter
FM-603 | Story | E06 | Date Pickers Replace Raw Text (Sessions, Goals, Challenges) | As a user, I want proper date pickers when entering dates, so that I never see 'NaN days left' from invalid input. | Should Have | P1 | 3 | Eagle 3 | Mid Dev | To Do | AC1: Given I am proposing a session, When I need to enter a date, Then a native DatePicker component appears (not a TextInput) AC2: Given I am creating a goal with a deadline, When I enter the date, Then a DatePicker is shown and past dates are rejected AC3: Given I am creating a challenge with an end date, When I enter the date, Then a DatePicker is shown and past dates are rejected | • Verify DatePicker appears on session propose, goal create, challenge create • Verify past dates are visually disabled and cannot be selected • Verify selected date is stored in correct YYYY-MM-DD format • Verify 'NaN days left' no longer appears anywhere in the app | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • DatePicker integration style for sessions, goals, challenges Designer delivers: DatePicker style guidance | ☐ DatePicker on all 3 locations ☐ Past dates disabled ☐ Correct format stored ☐ No 'NaN' anywhere
E07 | Epic | — | Security & App Store Compliance | Epic: Security & App Store Compliance
FM-701 | Story | E07 | iOS In-App Purchase for Pro Subscription | As a user on iOS, I want to subscribe to Pro via Apple's payment system, so that the app complies with App Store rules and my purchase is managed through my Apple account. | Must Have | P0 | 8 | Eagle 3 | Senior Dev | To Do | AC1: Given I am on iOS and tap 'Go Pro', When the purchase flow starts, Then it uses react-native-iap to present Apple's native purchase sheet AC2: Given I complete the purchase, When the transaction is verified, Then my is_pro flag is set to true and Pro features are unlocked AC3: Given I am on Android, When I tap 'Go Pro', Then Stripe web checkout is still used (Android allows this) | • Verify iOS purchase uses IAP, not web Stripe • Verify purchase receipt is validated server-side • Verify Pro features unlock after successful purchase • Verify subscription shows in user's Apple subscriptions settings | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Pro purchase flow for iOS (IAP native sheet) Designer delivers: Purchase flow UX | ☐ iOS uses IAP ☐ Receipt validated server-side ☐ Pro features unlock after purchase
FM-702 | Story | E07 | Admin Actions to Supabase Edge Functions | As the product owner, I want admin operations secured server-side, so that no regular user can execute admin actions by manipulating client-side code. | Must Have | P0 | 5 | Eagle 3 | Senior Dev | To Do | AC1: Given an admin user taps 'Ban User', When the action executes, Then it calls a Supabase Edge Function (not a direct client update) AC2: Given a non-admin user, When they attempt to call the admin Edge Function, Then the function rejects with 403 Forbidden AC3: Given the Edge Function, When it runs, Then it uses the service-role key and verifies the caller's is_admin status from the database | • Verify admin actions call Edge Function, not direct Supabase update • Verify Edge Function rejects non-admin callers • Verify is_admin check happens on server, not client | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Backend security | ☐ Admin calls Edge Function ☐ Non-admin rejected with 403 ☐ Server-side is_admin check
FM-703 | Story | E07 | Search Input Sanitization (Injection Fix) | As a user, I want search to be safe and secure, so that crafted inputs cannot manipulate database queries. | Must Have | P0 | 3 | Eagle 3 | Senior Dev | To Do | AC1: Given I type a search query, When the query is sent to Supabase, Then the input is sanitized (special characters escaped) or routed through an RPC function AC2: Given I enter a malicious string like '%,id.neq.', When the search executes, Then only legitimate matching usernames are returned | • Verify special characters in search don't alter query logic • Verify injection attempt returns no results (not all results) • Verify search still works correctly for normal queries | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Security fix | ☐ Special chars don't alter query ☐ Injection returns no results ☐ Normal search still works
FM-704 | Story | E07 | Terms & Privacy Policy (Tappable Links + Real Documents) | As a user, I want to read the actual Terms of Service and Privacy Policy, so that I know how my data is used before agreeing. | Must Have | P0 | 3 | Eagle 3 | Mid Dev | To Do | AC1: Given I am on the Welcome or Register screen, When I see the legal text, Then 'Terms' and 'Privacy Policy' are tappable links (not plain text) AC2: Given I tap either link, When the browser opens, Then it navigates to real, hosted legal documents AC3: Given the Settings screen, When I look for legal links, Then Terms and Privacy Policy are accessible there too | • Verify links are tappable on Welcome, Register, and Settings • Verify links open actual hosted documents (not 404) • Verify documents cover data usage, deletion, and contact information | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Legal link placement on Welcome, Register, Settings Designer delivers: Link placement mockup | ☐ Links tappable on 3 screens ☐ Documents load (not 404) ☐ Content covers data usage + deletion
E08 | Epic | — | Theme & Visual Consistency | Epic: Theme & Visual Consistency
FM-801 | Story | E08 | Dark/Light Theme Audit — All Hardcoded Colors | As a user, I want both dark and light themes to look correct on every screen, so that the app feels polished and intentional. | Should Have | P1 | 5 | Eagle 4 | Mid Dev | To Do | AC1: Given I switch to dark mode, When I navigate through every screen, Then no white backgrounds, black text on dark backgrounds, or jarring color mismatches appear AC2: Given I switch to light mode, When I navigate through every screen, Then no dark tiles, invisible text, or broken contrast appears AC3: Given any color in any StyleSheet, When inspecting the code, Then all colors come from useTheme() — zero hardcoded hex values | • Walk through all 22 screens in dark mode — screenshot each • Walk through all 22 screens in light mode — screenshot each • Code review: grep for hardcoded hex colors in all .tsx files • Verify ConversationRow, Search, GymTile, Messages SafeAreaView all use theme | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Full theme audit — screenshot every screen in both modes Designer delivers: Theme audit report with issues | ☐ All 22 screens correct in dark mode ☐ All 22 screens correct in light mode ☐ Zero hardcoded hex colors in codebase
FM-802 | Story | E08 | Messages N+1 Query Optimization | As a user, I want the Messages screen to load quickly even with 50+ conversations, so that I don't wait for slow loading. | Should Have | P1 | 5 | Eagle 4 | Senior Dev | To Do | AC1: Given I have 50 accepted matches, When I open the Messages tab, Then the conversations load in under 2 seconds AC2: Given the Messages screen, When it loads data, Then it uses a single Supabase RPC or join query (not 3 queries per conversation) | • Verify Messages loads in <2s with 50 conversations • Verify total Supabase requests reduced from 90+ to 1-3 • Verify conversation data (last message, avatar, name) still displays correctly | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Performance optimization | ☐ Messages loads <2s with 50 conversations ☐ Requests reduced from 90+ to 1-3 ☐ Data still displays correctly
FM-803 | Story | E08 | Discover Pagination (Replace 80-User Hard Cap) | As a user, I want to discover all relevant users, not just the first 80, so that I don't miss potential workout partners. | Should Have | P1 | 5 | Eagle 4 | Senior Dev | To Do | AC1: Given there are 200+ users in my area, When I browse Discover, Then I can see all of them through cursor-based pagination or infinite scroll AC2: Given I scroll to the end of the current batch, When more users exist, Then a new batch loads automatically AC3: Given Discover in swipe mode, When I run out of cards, Then a refresh button or automatic reload shows the next batch | • Verify more than 80 users are accessible in list mode • Verify pagination loads smoothly without duplicates • Verify all 3 view modes (list, swipe, map) support refreshing | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • 'Load more' or infinite scroll indicator Designer review: Loading indicator style | ☐ >80 users accessible ☐ Pagination loads without duplicates ☐ All 3 view modes support refresh
FM-804 | Story | E08 | SwipeDeck PanResponder Fix (Allow Card Taps) | As a user, I want to tap on swipe cards to view profile details, so that I can learn about someone before deciding to connect. | Should Have | P1 | 3 | Eagle 4 | Senior Dev | To Do | AC1: Given I am in swipe mode on Discover, When I tap the info button or card body, Then the profile sheet opens AC2: Given I want to swipe, When I drag the card left or right, Then the swipe gesture still works correctly AC3: Given the PanResponder, When the code is reviewed, Then onStartShouldSetPanResponder no longer returns true unconditionally | • Verify tap on card opens profile sheet • Verify swipe left/right still works correctly • Verify info button tap fires correctly • Verify no gesture conflicts between tap and swipe | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Gesture fix only | ☐ Tap opens profile sheet ☐ Swipe still works ☐ No gesture conflicts
E09 | Epic | — | Input Validation & UX Polish | Epic: Input Validation & UX Polish
FM-901 | Story | E09 | Negative Value Validation (Age/Weight/Duration/Progress) | As a user, I want the app to reject obviously invalid inputs, so that my profile and stats show real data. | Should Have | P1 | 2 | Eagle 4 | Mid Dev | To Do | AC1: Given I edit my profile age, When I enter -5 or 0 or 999, Then inline validation rejects it with 'Please enter a valid age (13-120)' AC2: Given I log a workout duration, When I enter a negative number, Then it is clamped to minimum 1 AC3: Given I update challenge progress, When I enter -100, Then it is clamped to 0 | • Verify negative ages, weights, and durations are rejected • Verify boundary values (0, 1, max) are handled correctly | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Validation logic | ☐ Negative values rejected ☐ Boundary values handled
FM-902 | Story | E09 | Keyboard Handling on All Modals | As a user, I want all form modals to be usable with the keyboard open, so that I can always reach the submit button. | Should Have | P1 | 3 | Eagle 4 | Mid Dev | To Do | AC1: Given I open any modal with a text input (log workout, compose post, report bug), When the keyboard opens, Then the content scrolls and the submit button is visible above the keyboard | • Verify log workout modal is scrollable with keyboard open on small screen (iPhone SE) • Verify compose post modal submit button is reachable • Verify report bug modal in settings is usable with keyboard | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Layout fix | ☐ Submit button reachable with keyboard on iPhone SE
FM-903 | Story | E09 | Loading States on All Async Buttons | As a user, I want buttons to show they're working when I tap them, so that I know the app is responding and I don't tap again. | Should Have | P1 | 3 | Eagle 4 | Mid Dev | To Do | AC1: Given I tap any async action button (Connect, Accept, Send, Propose, Join, Leave), When the request is in-flight, Then the button shows a spinner and is disabled AC2: Given the request completes (success or failure), When the response is received, Then the button returns to its normal state | • Verify all async buttons show loading state (audit each screen) • Verify double-tap prevention works on all buttons • Verify buttons re-enable after failure (not stuck disabled) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • Loading spinner style on buttons Designer review: Quick review | ☐ All async buttons show loading state ☐ Double-tap prevented ☐ Buttons re-enable after failure
FM-904 | Story | E09 | useFocusEffect on Stale Screens | As a user, I want fresh data when I return to a tab, so that I see the latest matches, messages, and activity. | Should Have | P1 | 3 | Eagle 5 | Mid Dev | To Do | AC1: Given I accept a match on the Home screen, When I navigate to the Connections tab, Then the new connection is visible immediately AC2: Given I return to Discover after switching tabs, When the data is older than 30 seconds, Then it automatically refreshes AC3: Given any tab with stale data, When I return to it, Then the load function is called with a staleness check | • Verify Matches/Connections tab refreshes on focus • Verify Discover refreshes on focus if stale • Verify no unnecessary re-fetches when data is fresh (<30s) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 NO DESIGN NEEDED: Data refresh logic | ☐ Connections tab refreshes on focus ☐ Discover refreshes if stale ☐ No unnecessary re-fetches
E10 | Epic | — | Accessibility & Growth | Epic: Accessibility & Growth
FM-1001 | Story | E10 | Accessibility Labels on All Interactive Elements | As a user with a screen reader, I want all buttons, inputs, and cards to have accessibility labels, so that I can navigate and use the app. | Could Have | P2 | 5 | Eagle 5 | Mid Dev | To Do | AC1: Given any interactive element (button, card, input, toggle), When a screen reader is active, Then the element has a descriptive accessibilityLabel AC2: Given any button, When a screen reader reads it, Then accessibilityRole='button' is set AC3: Given the tab bar, When a screen reader navigates, Then each tab has a label describing its purpose | • Test full app flow with VoiceOver (iOS) and TalkBack (Android) • Verify all buttons announce their purpose • Verify form inputs announce their labels • Verify navigation is logical (no focus traps) | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Accessibility label guidelines • Focus order documentation Designer delivers: A11y annotation guide | ☐ VoiceOver full flow test ☐ TalkBack full flow test ☐ All buttons announce purpose ☐ No focus traps
FM-1002 | Story | E10 | Google Places Autocomplete for City | As a new user, I want city autocomplete during onboarding and profile edit, so that my location is accurate for matching. | Should Have | P1 | 3 | Eagle 5 | Mid Dev | To Do | AC1: Given I am on onboarding step 4 (City) or editing my profile city, When I start typing, Then Google Places autocomplete suggestions appear AC2: Given I select a suggestion, When it is saved, Then the standardized city name is stored (not a typo like 'new yrok') | • Verify autocomplete works on onboarding and profile edit • Verify selected city is stored in standardized format • Verify manual entry is still possible if autocomplete fails | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 DESIGN NEEDED: • Autocomplete dropdown style for city input Designer delivers: Autocomplete component mockup | ☐ Autocomplete works on onboarding + profile ☐ Standardized city name stored ☐ Manual entry fallback works
FM-1003 | Story | E10 | Circle Capacity Enforcement | As a circle creator, I want the max member limit to be enforced, so that circles don't grow beyond their intended size. | Could Have | P2 | 2 | Eagle 5 | Mid Dev | To Do | AC1: Given a circle has reached max_members, When another user tries to join, Then they see 'This circle is full' and the Join button is disabled AC2: Given a circle has no max_members set, When anyone tries to join, Then they can join without restriction | • Verify join is blocked when circle is at capacity • Verify correct member count displayed • Verify circles without max_members allow unlimited joins | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • 'Circle is full' state on join button Designer review: Disabled state | ☐ Join blocked at capacity ☐ Correct count displayed ☐ No-limit circles still work
FM-1004 | Story | E10 | Ended Challenges Block Progress Updates | As a user, I want ended challenges to prevent further progress updates, so that results are final and fair. | Could Have | P2 | 2 | Eagle 5 | Mid Dev | To Do | AC1: Given a challenge has passed its end_date, When I open the challenge detail, Then the progress form is disabled/hidden AC2: Given an ended challenge, When I view the leaderboard, Then final results are shown as-is with no update option | • Verify progress form is disabled after end_date • Verify ended challenges show final results • Verify active challenges still allow progress updates | ☐ All ACs verified (happy + failure path) ☐ Loading/error/success states exist ☐ No console errors or warnings ☐ Tested on iOS + Android ☐ Code reviewed with 1+ approval ☐ Theme verified in dark + light mode ☐ No hardcoded colors ☐ Accessibility labels on new elements | 🎨 MINIMAL DESIGN: • Ended challenge visual treatment Designer review: Disabled form state | ☐ Progress form disabled after end_date ☐ Final results shown ☐ Active challenges still work

## Sprint Plan
FLEXMATCHES — SPRINT PLAN (Eagles)
Sprint | Dates | MVP | Sprint Goal | Stories | Total Points | Senior Dev Pts | Mid Dev Pts | Key Risk
Eagle 0 | Week 1–2 | MVP-0 | Kill all trust-destroying bugs: error handling, destructive actions, streak fix, forgot password, onboarding race | 9 stories FM-101, FM-102, FM-103, FM-104, FM-201, FM-301, FM-302, FM-401, FM-402 | 44 | 33 | 11 | Scope creep from adjacent bugs discovered during fixes
Eagle 1 | Week 3–4 | MVP-0 | Complete auth hardening, account lifecycle, input validation, duplicate prevention | 5 stories FM-202, FM-203, FM-303, FM-304, FM-305 | 16 | 5 | 11 | Account deletion Edge Function may require Supabase Pro plan
Eagle 2 | Week 5–6 | MVP-1 | Wire all silent notification paths, deep linking, push token security, realtime filter | 5 stories FM-501, FM-502, FM-503, FM-504, FM-505 | 17 | 11 | 6 | Push testing requires 2 physical devices — no simulator testing
Eagle 3 | Week 7–8 | MVP-1/2 | Unify trust system, IAP compliance, admin security, date pickers, search injection fix | 7 stories FM-601, FM-602, FM-603, FM-701, FM-702, FM-703, FM-704 | 32 | 26 | 6 | IAP implementation complex; Apple review unpredictable (1-7 days)
Eagle 4 | Week 9–10 | MVP-2 | Theme audit, performance (N+1, pagination), swipe fix, input validation, keyboard handling | 7 stories FM-801, FM-802, FM-803, FM-804, FM-901, FM-902, FM-903 | 26 | 13 | 13 | N+1 query fix may require new Supabase RPC function
Eagle 5 | Week 11–12 | MVP-3 | Accessibility, city autocomplete, stale data refresh, circle/challenge fixes, growth features | 5 stories FM-904, FM-1001, FM-1002, FM-1003, FM-1004 | 15 | 0 | 15 | Accessibility scope is often underestimated — timebox strictly
TEAM CAPACITY
Senior Dev (Backend/Full-stack): ~20 story points per 2-week sprint
Mid Dev (Mobile/Frontend): ~16 story points per 2-week sprint
Total team capacity: ~36 points/sprint (30-32 effective after QA/meetings)
BA: Parallel documentation, AC refinement, test case writing each sprint
QA: Regression testing + exploratory testing + UAT sign-off each sprint
PO: Sprint planning, daily standups, sprint review, retrospective

## Definition of Done
FLEXMATCHES — DEFINITION OF DONE
# | Category | Criterion | Verified By | Evidence
1 | Product | All acceptance criteria met (Given/When/Then verified) | PO + QA | Demo walkthrough or test evidence
2 | Product | Happy path AND failure path tested | QA | Test results with screenshots
3 | UX | Loading, success, and error states exist | QA | Screenshot evidence for each state
4 | UX | Destructive actions require confirmation dialog | QA | UI behavior verification
5 | UX | Theme verified in BOTH dark and light mode | QA | Screenshots in both themes
6 | Engineering | TypeScript strict mode passes — no @ts-ignore or any types | Dev | Build log clean
7 | Engineering | All async calls wrapped in try/catch | Dev | Code review checklist
8 | Engineering | No console errors/warnings in dev mode | Dev | Console screenshot
9 | Engineering | No hardcoded hex colors (all from useTheme) | Dev | Code review grep
10 | Engineering | Loading states on all async buttons | Dev + QA | UI verification
11 | Security | RLS verified for new/changed data access patterns | Senior Dev | Policy review note
12 | Security | Input validation on all user inputs (client + server) | Dev + QA | Test evidence
13 | Quality | Code reviewed by at least 1 other dev | Dev | PR approval
14 | Quality | Tested on iOS (latest) + Android (latest) | QA | Device test log
15 | Quality | No new tech debt without a follow-up ticket | Dev + PO | Ticket link if applicable
16 | Data | Analytics events added for major actions | Dev | Event list updated
17 | Ops | Release notes / decision log updated | BA | Updated doc link

## Retrospective Template
FLEXMATCHES — SPRINT RETROSPECTIVE
Sprint: Eagle 0
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]
Sprint: Eagle 1
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]
Sprint: Eagle 2
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]
Sprint: Eagle 3
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]
Sprint: Eagle 4
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]
Sprint: Eagle 5
Sprint Goal | [What was the sprint goal?]
Planned Points | [X points planned]
Completed Points | [X points completed]
Velocity | [X% of planned]
What Went Well | 1. 2. 3.
What Didn't Go Well | 1. 2. 3.
What Will We Change | 1. [Action item + owner + deadline]
Blockers Encountered | 1.
Stakeholder Feedback (PO) | [PO notes from sprint review]
QA Summary | [X tests passed, Y failed, Z blocked]
Carry-Over Stories | [Any stories not completed]

## UAT Test Cases
FLEXMATCHES — UAT TEST CASES
UAT ID | Sprint | Linked Story | Journey Stage | Test Scenario | Test Type | Preconditions | Test Steps | Expected Result | Priority | Status | Tester | Notes
UAT-001 | Eagle 0 | FM-301 | Authentication | Forgot password with valid email | Positive | Existing user account | 1. Open Login 2. Tap "Forgot password?" 3. Enter valid email 4. Tap Send | Reset email sent; success message appears | Critical | Not Run |  | Access recovery
UAT-002 | Eagle 0 | FM-301 | Authentication | Forgot password with unknown email | Negative | Unknown email | 1. Open Login 2. Tap "Forgot password?" 3. Enter unknown email 4. Tap Send | Neutral safe message shown (no account enumeration) | High | Not Run |  | Security: no enumeration
UAT-003 | Eagle 0 | FM-302 | Onboarding | New signup always lands on onboarding | Positive | Fresh new account | 1. Register new account 2. Observe landing screen | User lands on onboarding, never on home directly | Critical | Not Run |  | Test 10 times for race condition
UAT-004 | Eagle 0 | FM-302 | Onboarding | Onboarding save failure preserves data | Negative | Simulated network failure | 1. Fill onboarding fields 2. Disable network 3. Tap "Let's go" | Alert shown; stays on step; entered data preserved | Critical | Not Run |  | No silent failure
UAT-005 | Eagle 0 | FM-302 | Onboarding | Incomplete profile user returns to onboarding | Edge | Partial profile user | 1. Log in with incomplete profile user | User resumes onboarding until required fields saved | High | Not Run |  | Resume logic
UAT-006 | Eagle 0 | FM-201 | Messaging | Delete messages clears chat only | Positive | Match with messages | 1. Swipe conversation 2. Tap "Delete messages" 3. Confirm | Messages removed; match row preserved with status=accepted | Critical | Not Run |  | Trust-critical
UAT-007 | Eagle 0 | FM-201 | Messaging | Unmatch is separate and clearly explained | Positive | Existing match | 1. Swipe conversation 2. Tap "Unmatch" 3. Read dialog 4. Confirm | Match status set to "unmatched"; conversation removed from list | Critical | Not Run |  | Distinct from declined
UAT-008 | Eagle 0 | FM-201 | Messaging | Cancel on destructive dialog makes no changes | Negative | Existing match | 1. Swipe conversation 2. Tap "Unmatch" 3. Tap Cancel | Dialog closes; no data changes; conversation unchanged | High | Not Run |  | Safety check
UAT-009 | Eagle 0 | FM-104 | Sessions | Session accept error shows toast, UI unchanged | Negative | Pending session + no network | 1. Open chat with pending session 2. Disable network 3. Tap Accept | Toast: "Could not update session"; session still shows as pending | Critical | Not Run |  | No false state
UAT-010 | Eagle 0 | FM-104 | Sessions | Double-tap on session button sends single request | Edge | Pending session | 1. Tap Accept rapidly twice | Only 1 server request made; button disabled after first tap | High | Not Run |  | Double-tap guard
UAT-011 | Eagle 0 | FM-401 | Activity | Consecutive day streak increments | Positive | User with yesterday check-in | 1. Check in Day 1 2. Check in Day 2 | Streak increases by 1 for valid consecutive day | High | Not Run |  | Trust metric
UAT-012 | Eagle 0 | FM-401 | Activity | Missed day resets streak | Negative | User with 2+ day gap | 1. Log Day 1 2. Skip Day 2 3. Log Day 3 | Streak resets to 1 (not continues from old value) | Critical | Not Run |  | Core trust mechanic
UAT-013 | Eagle 0 | FM-402 | Activity | Same-day duplicate does not inflate streak | Negative | Already checked in today | 1. Check in 2. Try check-in again same day | Streak does NOT increment; button shows "Checked in ✓" | Critical | Not Run |  | Anti-spam
UAT-014 | Eagle 0 | FM-402 | Activity | Quick Check-in spam (10 taps) | Edge | Home screen | 1. Tap Quick Check-in 10 times rapidly | Streak increments by 1 only; button disables after first | Critical | Not Run |  | Exploit prevention
UAT-015 | Eagle 0 | All | End-to-End | Full Eagle 0 regression: auth → discover → chat → session → streak | E2E | 2 test accounts + 2 devices | 1. Register 2. Onboarding 3. Discover 4. Match 5. Chat 6. Propose session 7. Accept 8. Check in 9. Verify streak | Entire flow works without silent failure, data loss, or broken navigation | Critical | Not Run |  | Primary release gate

## QA Defect Log
FLEXMATCHES — QA DEFECT LOG
Defect ID | Sprint Found | Linked Story | Linked UAT | Module/Screen | Issue Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | Owner | Notes
BUG-001 | [5 empty] | Critical | P0 |  |  |  | Open |  | Use one row per defect. Fill during QA testing.
BUG-002 | [5 empty] | High | P1 |  |  |  | Open |  | Use one row per defect. Fill during QA testing.
BUG-003 | [5 empty] | High | P1 |  |  |  | Open |  | Use one row per defect. Fill during QA testing.
BUG-004 | [5 empty] | Medium | P2 |  |  |  | Open |  | Use one row per defect. Fill during QA testing.
BUG-005 | [5 empty] | Medium | P2 |  |  |  | Open |  | Use one row per defect. Fill during QA testing.

## Dependencies & Blockers
FLEXMATCHES — DEPENDENCIES & BLOCKERS
ID | Type | Story/Epic | Depends On | Description | Impact if Blocked | Status | Owner | Resolution Date
DEP-001 | Dependency | FM-101 | FM-103 | FM-101 requires ErrorState component created by FM-103 | Cannot add error handling to any screen without the component | Resolved | Mid Dev | Eagle 0 Day 1
DEP-002 | Dependency | FM-402 | FM-401 | FM-402 uses lib/streak.ts helper created by FM-401 | Check-in button cannot use RPC without the helper | Open | Senior Dev
DEP-003 | Dependency | FM-401 | Supabase RPC | FM-401 requires log_checkin() RPC function deployed to Supabase | Streak logic cannot be atomic without server-side function | Resolved | PO | SQL deployed
DEP-004 | Blocker | FM-301 | UI Design | Forgot password screen needs mockup matching auth design system | Dev can build logic but screen layout needs designer approval | Open | UI Designer
DEP-005 | Blocker | FM-201 | PO Approval | Confirmation dialog copy needs PO sign-off before implementation | Wrong copy = user confusion on destructive actions | Open | PO
DEP-006 | Dependency | Eagle 1 | Eagle 0 | Eagle 1 stories assume all Eagle 0 error handling is in place | Building on broken foundation if Eagle 0 incomplete | Open | Team
DEP-007 | External | FM-701 (Eagle 3) | Apple | IAP requires Apple Developer account + App Store Connect setup | Cannot implement iOS payments without Apple approval | Not Started | PO
DEP-008 | External | FM-704 (Eagle 3) | Legal | Terms & Privacy Policy require lawyer review or Termly/iubenda | Cannot link to non-existent legal documents | Not Started | PO
DEP-009 | Dependency | FM-202 (Eagle 1) | Supabase Pro | Account deletion Edge Function may need Supabase Pro plan for service-role key | Cannot fully delete auth user without admin API access | Not Started | PO
DEP-010 | Technical | All Push Stories | EAS Build | Push notifications only work with EAS Build, NOT Expo Go | Cannot test push on simulator — need physical device + EAS build | Known | Senior Dev

## Release Readiness
FLEXMATCHES — RELEASE READINESS CHECKLIST
# | Category | Check Item | Owner | Status | Notes
1 | Code Quality | All sprint stories marked Done (DoD passed) | PO + QA
2 | Code Quality | No open P0 or P1 bugs | QA
3 | Code Quality | No console errors or warnings in release build | Dev
4 | Code Quality | TypeScript builds without errors | Dev
5 | Testing | All UAT test cases passed | QA
6 | Testing | Regression smoke test passed (critical paths) | QA
7 | Testing | Tested on iOS latest + Android latest | QA
8 | Testing | Tested on small screen (iPhone SE or equivalent) | QA
9 | Testing | Dark mode + Light mode verified on all changed screens | QA
10 | Security | No new RLS gaps introduced | Senior Dev
11 | Security | No hardcoded secrets or API keys in code | Dev
12 | Security | Push token handling verified (no leaks) | QA
13 | Release | Release notes written | BA
14 | Release | Version number bumped in app.json | Dev
15 | Release | EAS Build successful (iOS + Android) | Dev
16 | Release | App Store screenshots updated (if UI changed) | PO
17 | Release | Changelog / decision log updated | BA
18 | Compliance | Terms & Privacy Policy links work | QA
19 | Compliance | No App Store guideline violations | PO
20 | Stakeholder | PO sprint review completed — all stories accepted | PO
21 | Stakeholder | Retrospective completed — action items logged | Team
22 | Rollback | Rollback plan documented (how to revert if critical bug found) | Dev
23 | Monitoring | Crash reporting active (Sentry or equivalent) | Dev |  | Not yet set up — add to Eagle 2+
24 | Monitoring | Key analytics events firing correctly | Dev |  | Not yet set up — add to Eagle 2+

## Incidents & Hotfixes
FLEXMATCHES — PRODUCTION INCIDENT & HOTFIX LOG
Incident ID | Date | Severity | Title | Description | User Impact | Root Cause | Resolution | Hotfix Build | Time to Resolve | Owner | Post-Mortem
INC-001 |  | P0 |  |  |  |  | Template row — fill when production incidents occur |  |  |  | Always write a brief post-mortem: what happened, why, what we changed

## Decision Log
FLEXMATCHES — PRODUCT DECISION LOG
Decision ID | Date | Sprint | Decision | Rationale | Alternatives Considered | Made By | Impact
DEC-001 | 2026-04-02 | Pre-Sprint | Fix 102 QA issues before adding any new features | App scored 3.5/10 on readiness. Trust mechanics broken. No error handling. Growth on broken foundation wastes users. | Ship as-is and fix in parallel; Add features to attract users first | PO | 6-week hardening sprint before any growth work
DEC-002 | 2026-04-02 | Pre-Sprint | Use RICE + MoSCoW for prioritization | Need objective, data-driven prioritization — not emotional. RICE gives scores; MoSCoW gives classification. | Priority poker; Severity-only ordering; Feature voting | PO + BA | Every story has a defensible priority rationale
DEC-003 | 2026-04-02 | Pre-Sprint | Atomic streak via Supabase RPC (not client-side) | Client-side read-modify-write is exploitable and has race conditions. Server-side function is atomic and tamper-proof. | Client-side with optimistic lock; Supabase trigger | Senior Dev + PO | Streak trust mechanic is now reliable
DEC-004 | 2026-04-02 | Pre-Sprint | Add "unmatched" as distinct status (not reuse "declined") | Analytics needs to distinguish "never accepted" from "was connected, then unmatched". Same status = blind spot. | Reuse declined; Add timestamp-based distinction | BA + PO | Clean analytics on match lifecycle
DEC-005 | 2026-04-02 | Eagle 0 | Pull-to-refresh failure keeps existing data (no ErrorState replacement) | Replacing visible data with error state on refresh is jarring. User already has content — show toast instead. | Replace with ErrorState; Show inline error banner | Senior Dev | Better UX: existing data preserved during transient failures
DEC-006 | 2026-04-02 | Eagle 0 | Build ErrorState component before all other stories | FM-101 (8pts) needs ErrorState from FM-103 (3pts). Building foundation first avoids rework on 10 screens. | Build error handling inline per screen; Defer component extraction | BA + Senior Dev | Single reusable component used across all screens
DEC-007 | 2026-04-02 | Pre-Sprint | Sprint naming: Eagle 0, Eagle 1... (not Sprint 1, 2...) | Team identity and morale. "Eagle" aligns with the product's fitness/achievement theme. | Standard Sprint numbering; Animal names; Milestone names | PO | Team culture: every sprint has identity

## Metrics & KPIs
FLEXMATCHES — PRODUCT METRICS & KPIs
Metric | Category | Why It Matters | Current (est.) | Eagle 2 Target | Eagle 4 Target | 12-Month Target | Instrumentation
Signup Completion Rate | Acquisition | Top-of-funnel friction | Unknown (no analytics) | > 70% | > 80% | > 85% | signup_started → signup_completed
Onboarding Completion Rate | Activation | Profile quality for matching | Unknown | > 65% | > 75% | > 85% | onboarding_started → onboarding_step_N → onboarding_completed
First Match Request Sent | Activation | Discovery creates action | Unknown | > 40% | > 50% | > 60% | discover_viewed → request_sent
First Message Sent | Engagement | Matches become conversations | Unknown | > 50% | > 60% | > 70% | match_accepted → first_message_sent
Session Proposal Rate | Engagement | Users move beyond chat | Unknown | > 25% | > 35% | > 45% | session_proposed (per matched pair)
Session Completion Rate | Value | North star: real-world meetups | Unknown | > 20% | > 30% | > 40% | session_completed / session_accepted
D7 Retention | Retention | Product earns a habit | Unknown | > 25% | > 35% | > 50% | Cohort analysis: return within 7 days
D30 Retention | Retention | Long-term value | Unknown | > 10% | > 20% | > 30% | Cohort analysis: return within 30 days
Crash-Free Rate | Quality | App stability | Unknown | > 95% | > 99% | > 99.5% | Sentry crash reports
Push Notification Open Rate | Engagement | Notifications are relevant | Unknown | > 15% | > 20% | > 25% | push_sent → push_opened
App Store Rating | Quality | Discoverability + trust | Not yet rated | > 3.5★ | > 4.0★ | > 4.5★ | App Store Connect
Support Incident Rate | Quality | Trust cost from defects | Unknown | < 10 per 100 WAU | < 5 per 100 WAU | < 2 per 100 WAU | Support tickets / WAU
Pro Conversion Rate | Revenue | Monetization health | 0% | > 2% | > 5% | > 8% | pro_viewed → pro_purchased
Average Sessions per Match/Month | Value | Core value delivery | Unknown | > 1.0 | > 2.0 | > 4.0 | sessions_completed / active_matches

## App Store & Compliance
FLEXMATCHES — APP STORE & COMPLIANCE CHECKLIST
# | Category | Requirement | Status | Blocker? | Owner | Target Sprint
1 | Apple Mandatory | In-App Purchase for digital goods (Pro subscription) | ❌ Not Done | YES — Apple will reject | Senior Dev | Eagle 3
2 | Apple Mandatory | Forgot Password flow available | ❌ Not Done (building in Eagle 0) | YES — Apple may reject | Mid Dev | Eagle 0
3 | Apple Mandatory | Privacy Policy accessible from app | ❌ Not tappable | YES — Apple requires | Mid Dev + PO | Eagle 3
4 | Apple Mandatory | Terms of Service accessible from app | ❌ Not tappable | YES — Apple requires | Mid Dev + PO | Eagle 3
5 | Apple Mandatory | Account deletion available | ⚠️ Partial (profile deleted, auth user remains) | YES — Apple requires full deletion | Senior Dev | Eagle 1
6 | Apple Mandatory | Test account credentials for review | ❌ Not provided (TODO in App Store listing) | YES — reviewer needs login | PO | Before submission
7 | Apple Review | App functions without crash on reviewer device | ⚠️ Risk (no error boundary before Eagle 0) | Potential rejection | QA | Eagle 0
8 | Apple Review | No placeholder content or broken links | ⚠️ Legal links are broken | Potential rejection | PO | Eagle 3
9 | GDPR | User can export their data | ❌ Not implemented | Required for EU users | Senior Dev | Eagle 4+
10 | GDPR | User can delete their account and all data | ⚠️ Partial | Required for EU users | Senior Dev | Eagle 1
11 | GDPR | Privacy policy covers data collection, usage, sharing | ❌ No policy exists | Required | PO + Legal | Eagle 3
12 | CCPA | California users can opt out of data selling | N/A — we don't sell data | Not a blocker | PO | Document in policy
13 | App Store Optimization | Keywords set (100 chars max) | ✅ Done | No | PO | Done
14 | App Store Optimization | Screenshots prepared | ⚠️ May need update after Eagle 0 | No | PO | After Eagle 0
15 | App Store Optimization | App preview video | ❌ Not created | No | PO | After Eagle 2
16 | Security | No API keys in client code | ✅ Uses .env (not committed) | No | Dev | Done
17 | Security | RLS policies on all sensitive tables | ⚠️ Not fully audited | Potential data leak | Senior Dev | Eagle 2
18 | Security | Admin actions server-side only | ❌ Client-side only | Security risk | Senior Dev | Eagle 3
19 | Push | Push notification permission requested at appropriate time | ⚠️ Requested too early (before signup) | UX issue | Mid Dev | Eagle 2
20 | Push | Push tokens cleaned on logout | ❌ Not implemented | Privacy risk | Senior Dev | Eagle 2
21 | Location | Location permission explained to user | ⚠️ No explanation before request | UX issue | Mid Dev | Eagle 4
22 | Location | Location not saved without consent | ⚠️ GPS silently saved to profile | Privacy issue | Senior Dev | Eagle 4